## OOP TS Milestone TestCases
DE4A Test Cases
| OOP TS Milestone 2 | “Hello Europe” between two connected Member States (Sweden and Romania)
| OBJECTIVE | Show the message flow between 2 different member states can be done uninterrupted and a valid request and response can be send of the OOP TS infrastructure between 2 member states
| PRECONDITIONS | The testing of OOP TS milestone 1 has been completed succesfully, meaning: * Component testing on the OOP TS common components has been succesful in both Member States * national integration Testing on the deployment of the common components has been succesful (DE Mock - DE4A Connector, DO-mock - DE4A Connector) in both member states * This has been verified with the eGOVLab testing grounds.
COMPONENTS
| COMPONENT | TYPE | COMMENTS
| Data Evaluator (MS1) | Mocked | The DE in this case must be a version that can send an evidence request with a specific eIDASLegal Identifier and also be able to receive the actual response from the DE4A Connector and be able to show/log the results
| DE4A Connector (DR - MS1) | Released version WP5 | A working and configured DE4A Connetor in the role as Data Requester, that has been proved to work in combination with the eGOVLab Testing grounds
| AS/4 Gateway (MS2) | Real | A working and configured AS/4 gateway, which is either the one included in the DE4A connector or an own implementation and must be show to be working in combination with the eGOVLab testing grounds
| SMP | Hosted by eGovLab WP5 | The SMP is hosted by eGOVLab, but must contain the informtion of the MS1 en MS2 AS/4 Gateway information and the Data Evaluator and Data Owner indentities and urls
| ESL/IDK (MS1 en MS2) | local up-to-date config file | Both member states must have a local ESL/IDK configuration "file", that contains the entries of the DE(MS1) and DO(MS2)
| DNS | Registered by MS | The right dns registrations must have been made for the DE and DO and be reachable by the DE4A connector of the relevant member state
| SML | Registered by WP5 | Ensure the SML is filled with the relevant data of the AS/4 gateways of MS1 and MS2
| AS/4 Gateway (MS2) | Real | A working and configured AS/4 gateway, which is either the one included in the DE4A connector or an own implementation and must be show to be working in combination with the eGOVLab testing grounds
| DE4A Connector (DT - MS2) | Released version WP5 | A working and configured DE4A Connetor in the role as Data Transferrer, that has been proved to work in combination with the eGOVLab Testing grounds
| Data Owner (MS2) | Mocked | A mocked DO, that can respond to DE4A connector request and provide the evidence or the specific eIDASLegalIdentifiers, or respond with "Not Found"
OOP TS Milestone 2 - TEST CASES
# | Test Case | Test | Test Case parameters | Actions & Conditions | Expected Result | Actual Result | Comments
|  | Description |  |  | Response Status
Response Type
TESTLAB Validation
1 | TC.OOPTS.MS2.TL.11A | An evidence request from the (mocked) Data Evaluator of member state A, using the eIDASLegalIdentifer of the Teslab, which is answered by the (mocked) Data Owner of the Testlab with informtion related to the eIDASLegalIdentifier of the Testlab and received by the requesting Data Evaluator of member state A
|  |  | (mocked) Data Evaluator in member state 1 registered in the SMP/IDK | Send request for evidence for eIDASLegalIdentifier | A "Success" status response at the Data Evaluator |  | Provide a screen shot of the send request. Please provide the test evidence of a succesful test in the form of a screenshot of the Mocked DE and the received Response XML at the Mocked DE And also provide the Kafka logs (can be screenshots) from both Member State that show the handling of the messages
|  |  | IDK/ESL configuration (file) | For a regsitered (mocked) Data Owner in the IDK/ESL | With evidence related the eIDASLegalIdentifier
|  |  | DE4A Connector (DR) in member state A | To the DE4A Connector (Data tranferrer) of member state A
|  |  | AS/4 gateway in member state A | That is transferred to the AS/4 gateway of the Testlab
|  |  | e-GovLab SMP (Test Lab) | using the information found in the eGovLab SMP
|  |  | AS/4 gateway of the Testlab | And received by the AS/4 gateway in the Testlab and transferred to the DE4A Connector (DT) of the Testlab
|  |  | DE4A Connector (DT) in the Testlab | Received by the DE4A (DT) connector in the Testlab and transferred to the (mocked) Data Owner of the Testlab
|  |  | (mocked) Data Owner in the Testlab registered in the SMP/IDK | Receives the reuqest and answer with the requested evidence type for the specific eIDASLegalIdentifier in the request and sends this request back to the DE4A Connector (DT)
HAPPY FLOW
2 | TC.OOPTS.MS2.HPY.11A | An evidence request from the (mocked) Data Evaluator of member state A, using an eIDASLegalIdentifer for member state B, which is answered by the (mocked) Data Owner of member state B with informtion related to the eIDASLegalIdentifier and received by the requesting Data Evaluator of member state A
|  |  | (mocked) Data Evaluator in member state 1 registered in the SMP/IDK | Send request for evidence for eIDASLegalIdentifier | A "Success" status response at the Data Evaluator |  | Provide a screen shot of the send request. Please provide the test evidence of a succesful test in the form of a screenshot of the Mocked DE and the received Response XML at the Mocked DE And also provide the Kafka logs (can be screenshots) from both Member State that show the handling of the messages
|  |  | IDK/ESL configuration (file) | For a regsitered (mocked) Data Owner in the IDK/ESL | With evidence related the eIDASLegalIdentifier
|  |  | DE4A Connector (DR) in member state A | To the DE4A Connector (Data tranferrer) of member state A
|  |  | AS/4 gateway in member state A | That is transferred to the AS/4 gateway of member state B
|  |  | e-GovLab SMP (Test Lab) | using the information found in the eGovLab SMP
|  |  | AS/4 gateway in member state B | And received by the AS/4 gateway in member state B and transferred to the DE4A Connector (DT) of membe-state B
|  |  | DE4A Connector (DT) in member state B | Received by the DE4A (DT) connector in member state B and transferred to the (mocked) Data Owner
|  |  | (mocked) Data Owner in member state B registered in the SMP/IDK | Receives the reuqest and answer with the requested evidence type for the specific eIDASLegalIdentifier in the request and sends this request back to the DE4A Connector (DT)
NO MATCHING EIDASLEGALIDENTIFIER
3 | TC.OOPTS.MS2.NELI.11A | An evidence request from the (mocked) Data Evaluator of one pilot member state A, using an eIDASLegalIdentifer from membe state B, which is answered by the (mocked) Data Owner of member state B with the status "Not found"
|  |  | (mocked) Data Evaluator in member state 1 registered in the SMP/IDK | Send request for evidence for eIDASLegalIdentifier | A "Not found" status response at the Data Evaluator |  | Provide a screen shot of the send request. Please provide the test evidence of a succesful test in the form of a screenshot of the Mocked DE and the received Response XML at the Mocked DE And also provide the Kafka logs (can be screenshots) from both Member State that show the handling of the messages
|  |  | IDK/ESL configuration (file) | For a regsitered (mocked) Data Owner in the IDK/ESL | Without evidence related the eIDASLegalIdentifier
|  |  | DE4A Connector (DR) in member state A | To the DE4A Connector (Data tranferrer) of member state A
|  |  | AS/4 gateway in member state A | That is transferred to the AS/4 gateway of member state B
|  |  | e-GovLab SMP (Test Lab) | using the information found in the eGovLab SMP
|  |  | AS/4 gateway in member state B | And received by the AS/4 gateway in member state B and transferred to the DE4A Connector (DT) of membe-state B
|  |  | DE4A Connector (DT) in member state B | Received by the DE4A (DT) connector in member state B and transferred to the (mocked) Data Owner
|  |  | (mocked) Data Owner in member state B registered in the SMP/IDK | Receives the reuqest and answers with "Not found" as the specific eIDASLegalIdentifier in the request does not match any records and sends this request back to the DE4A Connector (DT)
NO RESPONSE
4 | TC.OOPTS.MS2.NR.11A | An evidence request from the (mocked) Data Evaluator of pilot member state A, using an eIDASLegalIdentifer of member state B, which can not be answered by a (mocked) Data Owner, as it's offline. The DE4A DT of member state B responses with "Not Available"
|  |  | (mocked) Data Evaluator in member state 1 registered in the SMP/IDK | Send request for evidence for eIDASLegalIdentifier | A "Not availble" status response at the Data Evaluator |  | Provide a screen shot of the send request. Please provide the test evidence of a succesful test in the form of a screenshot of the Mocked DE and the received Response XML at the Mocked DE And also provide the Kafka logs (can be screenshots) from both Member State that show the handling of the messages
|  |  | IDK/ESL configuration (file) | For a regsitered (mocked) Data Owner in the IDK/ESL | Without evidence related the eIDASLegalIdentifier
|  |  | DE4A Connector (DR) in member state A | To the DE4A Connector (Data tranferrer) of member state A
|  |  | AS/4 gateway in member state A | That is transferred to the AS/4 gateway of member state B
|  |  | e-GovLab SMP (Test Lab) | using the information found in the eGovLab SMP
|  |  | AS/4 gateway in member state B | And received by the AS/4 gateway in member state B and transferred to the DE4A Connector (DT) of membe-state B
|  |  | DE4A Connector (DT) in member state B | Received by the DE4A (DT) connector in member state B and transferred to the (mocked) Data Owner
|  |  | (mocked) Data Owner in member state B registered in the SMP/IDK | Is not available (off-line). In this case the DE4A (DT) should provide a "Not available" esponse back to the Data Evaluator

## Test Results
Test Results
OOP TS Milestone 2 - TEST CASES
# | Test Case | Test | Test Case parameters |  |  | Actions & Conditions | Expected Result | Actual Result | Comments
|  | Description |  |  |  |  | Response Status
Response Type
TESTLAB Validation
1 | TC.OOPTS.MS2.TL.11A | An evidence request from the (mocked) Data Evaluator of member state A, using the eIDASLegalIdentifer of the Teslab, which is answered by the (mocked) Data Owner of the Testlab with informtion related to the eIDASLegalIdentifier of the Testlab and received by the requesting Data Evaluator of member state A
| Testing member state | Result
| AT | Success
| NL | Success
RO
NL
HAPPY FLOW
2 | TC.OOPTS.MS2.HPY.11A | An evidence request from the (mocked) Data Evaluator of member state A, using an eIDASLegalIdentifer for member state B, which is answered by the (mocked) Data Owner of member state B with informtion related to the eIDASLegalIdentifier and received by the requesting Data Evaluator of member state A
| Member state A | AT | NL | RO | SE
Member State B
AT
| NL |  |  | Success
| RO |  | Success
SE
NO MATCHING EIDASLEGALIDENTIFIER
3 | TC.OOPTS.MS2.NELI.11A | An evidence request from the (mocked) Data Evaluator of one pilot member state A, using an eIDASLegalIdentifer from membe state B, which is answered by the (mocked) Data Owner of member state B with the status "Not found"
| Member state A | AT | NL | RO | SE
Member State B
AT
| NL |  |  | Success
| RO |  | Success
SE
NO RESPONSE
4 | TC.OOPTS.MS2.NR.11A | An evidence request from the (mocked) Data Evaluator of pilot member state A, using an eIDASLegalIdentifer of member state B, which can not be answered by a (mocked) Data Owner, as it's offline. The DE4A DT of member state B responses with "Not Available"
| Member state A | AT | NL | RO | SE
Member State B
AT
| NL |  |  | Success
| RO |  | Success
SE

## TestLab Information
TestLab Information
REQUIRED INFORMATION BEFORE THE TEST CAN START
INFORMATION | TYPE | eGovLab/Spain |  | COMMENTS
TestLab mock DE User interface | URL | Provide the information here before the tests... | This is the URL of the WP5 Testlab Mocked DE, which is used for the Testlab validation test to query the memberstat's (mocked) DO
Teslab mock DO identifier | URL | Provide the information here before the tests... | This is the OOP identifier of the Mock DO in the Teslab of WP5 (required for making a request from the WP5 Teslab Mocked DE)
TestLab eIDASLegalIdentifier | Identifier | Provide the information here before the tests... | This is a eIDASLegalIdentifier that can be used in the Teslab validation test at the memberstate (mocked) DE

## AT Information
AT Information
REQUIRED INFORMATION BEFORE THE TEST CAN START
INFORMATION | TYPE | Member State |  | COMMENTS
TestLab mock DE User interface | URL | Provide the information here before the tests... | This is the URL of the WP5 Testlab Mocked DE, which is used for the Testlab validation test to query the memberstat's (mocked) DO
Teslab mock DO identifier | URL | Provide the information here before the tests... | This is the OOP identifier of the Mock DO in the Teslab of WP5 (required for making a request from the WP5 Teslab Mocked DE)
TestLab eIDASLegalIdentifier | Identifier | Provide the information here before the tests... | This is a eIDASLegalIdentifier that can be used in the Teslab validation test at the memberstate (mocked) DE
DE url (User Interface) | URL | Optional for reference | This is the url to the Mocked DE, that host the user interface with which the request can be send
DE url | URL | Provide the information here before the tests... | This is the url of the (mocked) DE that will be sending the request and receving the evidence or other answer. I's needed for registration in the SMP of eGOVLab and must be registered before the tests proceed
DE identifier | Identifier | Provide the information here before the tests... | This is the OOP identifier as for the DE Mock, this indentifier must be known in themember states local ESL/IDK config "file" of the DE4A Connector and the eGOVLab SMP, before the test can proceed
DE4A Connector url | URL | Optional for reference | This is the url of the DE4A Connector of the member state. It's captured for reference, but it's not a prerequisites for he tests. The member states shoudl have properly configured the connection betwen the DE and DE4A connector beforehand already.
AS/4 gateway url | URL | Provide the information here before the tests... | This is the URL of the member states AS/4 gateway and must be know and registered in the SML and SMP of eGOVLab before the tests proceed.
AS/4 gateway certificate | Certificate | Provide the information here before the tests... | This is the certificate used by the AS/4 gateway to identify itself with and addtionally encrypt the messages between the two AS/4 gateways of the member states. It mus be regsitered in the SML/SMP before the tests begin and trusted on each end on the AS/4 gateways.
DO url | URL | Provide the information here before the tests... | This is the url of the (mocked) DO that will be responding to the DE requests, It's needed for registration in thee SMP of eGOVLab and must be registered before the tetst proceed
DO identifier | Identifier | Provide the information here before the tests... | This is the OOP identifier as for the DE Mock, this indentifier must be known in themember states local ESL/IDK config "file" of the DE4A Connector and the eGOVLab SMP, before the test can proceed
eIDASLegalIdentifier-1 | Identifier | Provide the information here before the tests... | This is an eIDASLegalIdentifier for which the other memberstate's DO can provide evidence
eIDASLegalIdentifier-2 | Identifier | Provide the information here before the tests... | This is an eIDASLegalIdentifier for which the other memberstate's DO cannot provide evidence
Properly filled ESL/IDK | Config file | This must be completed before the tests | Both member states must have a properly filled ESL/IDK config "file", which contains the identities of the (mocked) DE and DO's of both member states and have registered the proper evidence type supported.
Properly filled SMP | Config | This must be completed before the tests | Both member states must assure they have their DE and DO information (identity, url and evidence type) regsitered in the SMP of eGOVLab
Properly filled SML | Config | This must be completed before the tests | Both member states must assure they have their AS/4 gateways properly regsitered (url, certificate, identifier) in the eGOVLab SML, so their routing informtion can be found by the other AS/4 gateways

## NL Information
AT Information
REQUIRED INFORMATION BEFORE THE TEST CAN START
INFORMATION | TYPE | Member State |  | COMMENTS
TestLab mock DE User interface | URL | Provide the information here before the tests... | This is the URL of the WP5 Testlab Mocked DE, which is used for the Testlab validation test to query the memberstat's (mocked) DO
Teslab mock DO identifier | URL | Provide the information here before the tests... | This is the OOP identifier of the Mock DO in the Teslab of WP5 (required for making a request from the WP5 Teslab Mocked DE)
TestLab eIDASLegalIdentifier | Identifier | Provide the information here before the tests... | This is a eIDASLegalIdentifier that can be used in the Teslab validation test at the memberstate (mocked) DE
DE url (User Interface) | URL | Optional for reference | This is the url to the Mocked DE, that host the user interface with which the request can be send
DE url | URL | Provide the information here before the tests... | This is the url of the (mocked) DE that will be sending the request and receving the evidence or other answer. I's needed for registration in the SMP of eGOVLab and must be registered before the tests proceed
DE identifier | Identifier | Provide the information here before the tests... | This is the OOP identifier as for the DE Mock, this indentifier must be known in themember states local ESL/IDK config "file" of the DE4A Connector and the eGOVLab SMP, before the test can proceed
DE4A Connector url | URL | Optional for reference | This is the url of the DE4A Connector of the member state. It's captured for reference, but it's not a prerequisites for he tests. The member states shoudl have properly configured the connection betwen the DE and DE4A connector beforehand already.
AS/4 gateway url | URL | Provide the information here before the tests... | This is the URL of the member states AS/4 gateway and must be know and registered in the SML and SMP of eGOVLab before the tests proceed.
AS/4 gateway certificate | Certificate | Provide the information here before the tests... | This is the certificate used by the AS/4 gateway to identify itself with and addtionally encrypt the messages between the two AS/4 gateways of the member states. It mus be regsitered in the SML/SMP before the tests begin and trusted on each end on the AS/4 gateways.
DO url | URL | Provide the information here before the tests... | This is the url of the (mocked) DO that will be responding to the DE requests, It's needed for registration in thee SMP of eGOVLab and must be registered before the tetst proceed
DO identifier | Identifier | Provide the information here before the tests... | This is the OOP identifier as for the DE Mock, this indentifier must be known in themember states local ESL/IDK config "file" of the DE4A Connector and the eGOVLab SMP, before the test can proceed
eIDASLegalIdentifier-1 | Identifier | Provide the information here before the tests... | This is an eIDASLegalIdentifier for which the other memberstate's DO can provide evidence
eIDASLegalIdentifier-2 | Identifier | Provide the information here before the tests... | This is an eIDASLegalIdentifier for which the other memberstate's DO cannot provide evidence
Properly filled ESL/IDK | Config file | This must be completed before the tests | Both member states must have a properly filled ESL/IDK config "file", which contains the identities of the (mocked) DE and DO's of both member states and have registered the proper evidence type supported.
Properly filled SMP | Config | This must be completed before the tests | Both member states must assure they have their DE and DO information (identity, url and evidence type) regsitered in the SMP of eGOVLab
Properly filled SML | Config | This must be completed before the tests | Both member states must assure they have their AS/4 gateways properly regsitered (url, certificate, identifier) in the eGOVLab SML, so their routing informtion can be found by the other AS/4 gateways

## RO Information
AT Information
REQUIRED INFORMATION BEFORE THE TEST CAN START
INFORMATION | TYPE | Member State |  | COMMENTS
TestLab mock DE User interface | URL | Provide the information here before the tests... | This is the URL of the WP5 Testlab Mocked DE, which is used for the Testlab validation test to query the memberstat's (mocked) DO
Teslab mock DO identifier | URL | Provide the information here before the tests... | This is the OOP identifier of the Mock DO in the Teslab of WP5 (required for making a request from the WP5 Teslab Mocked DE)
TestLab eIDASLegalIdentifier | Identifier | Provide the information here before the tests... | This is a eIDASLegalIdentifier that can be used in the Teslab validation test at the memberstate (mocked) DE
DE url (User Interface) | URL | Optional for reference | This is the url to the Mocked DE, that host the user interface with which the request can be send
DE url | URL | Provide the information here before the tests... | This is the url of the (mocked) DE that will be sending the request and receving the evidence or other answer. I's needed for registration in the SMP of eGOVLab and must be registered before the tests proceed
DE identifier | Identifier | Provide the information here before the tests... | This is the OOP identifier as for the DE Mock, this indentifier must be known in themember states local ESL/IDK config "file" of the DE4A Connector and the eGOVLab SMP, before the test can proceed
DE4A Connector url | URL | Optional for reference | This is the url of the DE4A Connector of the member state. It's captured for reference, but it's not a prerequisites for he tests. The member states shoudl have properly configured the connection betwen the DE and DE4A connector beforehand already.
AS/4 gateway url | URL | Provide the information here before the tests... | This is the URL of the member states AS/4 gateway and must be know and registered in the SML and SMP of eGOVLab before the tests proceed.
AS/4 gateway certificate | Certificate | Provide the information here before the tests... | This is the certificate used by the AS/4 gateway to identify itself with and addtionally encrypt the messages between the two AS/4 gateways of the member states. It mus be regsitered in the SML/SMP before the tests begin and trusted on each end on the AS/4 gateways.
DO url | URL | Provide the information here before the tests... | This is the url of the (mocked) DO that will be responding to the DE requests, It's needed for registration in thee SMP of eGOVLab and must be registered before the tetst proceed
DO identifier | Identifier | Provide the information here before the tests... | This is the OOP identifier as for the DE Mock, this indentifier must be known in themember states local ESL/IDK config "file" of the DE4A Connector and the eGOVLab SMP, before the test can proceed
eIDASLegalIdentifier-1 | Identifier | Provide the information here before the tests... | This is an eIDASLegalIdentifier for which the other memberstate's DO can provide evidence
eIDASLegalIdentifier-2 | Identifier | Provide the information here before the tests... | This is an eIDASLegalIdentifier for which the other memberstate's DO cannot provide evidence
Properly filled ESL/IDK | Config file | This must be completed before the tests | Both member states must have a properly filled ESL/IDK config "file", which contains the identities of the (mocked) DE and DO's of both member states and have registered the proper evidence type supported.
Properly filled SMP | Config | This must be completed before the tests | Both member states must assure they have their DE and DO information (identity, url and evidence type) regsitered in the SMP of eGOVLab
Properly filled SML | Config | This must be completed before the tests | Both member states must assure they have their AS/4 gateways properly regsitered (url, certificate, identifier) in the eGOVLab SML, so their routing informtion can be found by the other AS/4 gateways

## SE Information
AT Information
REQUIRED INFORMATION BEFORE THE TEST CAN START
INFORMATION | TYPE | Member State |  | COMMENTS
TestLab mock DE User interface | URL | Provide the information here before the tests... | This is the URL of the WP5 Testlab Mocked DE, which is used for the Testlab validation test to query the memberstat's (mocked) DO
Teslab mock DO identifier | URL | Provide the information here before the tests... | This is the OOP identifier of the Mock DO in the Teslab of WP5 (required for making a request from the WP5 Teslab Mocked DE)
TestLab eIDASLegalIdentifier | Identifier | Provide the information here before the tests... | This is a eIDASLegalIdentifier that can be used in the Teslab validation test at the memberstate (mocked) DE
DE url (User Interface) | URL | Optional for reference | This is the url to the Mocked DE, that host the user interface with which the request can be send
DE url | URL | Provide the information here before the tests... | This is the url of the (mocked) DE that will be sending the request and receving the evidence or other answer. I's needed for registration in the SMP of eGOVLab and must be registered before the tests proceed
DE identifier | Identifier | Provide the information here before the tests... | This is the OOP identifier as for the DE Mock, this indentifier must be known in themember states local ESL/IDK config "file" of the DE4A Connector and the eGOVLab SMP, before the test can proceed
DE4A Connector url | URL | Optional for reference | This is the url of the DE4A Connector of the member state. It's captured for reference, but it's not a prerequisites for he tests. The member states shoudl have properly configured the connection betwen the DE and DE4A connector beforehand already.
AS/4 gateway url | URL | Provide the information here before the tests... | This is the URL of the member states AS/4 gateway and must be know and registered in the SML and SMP of eGOVLab before the tests proceed.
AS/4 gateway certificate | Certificate | Provide the information here before the tests... | This is the certificate used by the AS/4 gateway to identify itself with and addtionally encrypt the messages between the two AS/4 gateways of the member states. It mus be regsitered in the SML/SMP before the tests begin and trusted on each end on the AS/4 gateways.
DO url | URL | Provide the information here before the tests... | This is the url of the (mocked) DO that will be responding to the DE requests, It's needed for registration in thee SMP of eGOVLab and must be registered before the tetst proceed
DO identifier | Identifier | Provide the information here before the tests... | This is the OOP identifier as for the DE Mock, this indentifier must be known in themember states local ESL/IDK config "file" of the DE4A Connector and the eGOVLab SMP, before the test can proceed
eIDASLegalIdentifier-1 | Identifier | Provide the information here before the tests... | This is an eIDASLegalIdentifier for which the other memberstate's DO can provide evidence
eIDASLegalIdentifier-2 | Identifier | Provide the information here before the tests... | This is an eIDASLegalIdentifier for which the other memberstate's DO cannot provide evidence
Properly filled ESL/IDK | Config file | This must be completed before the tests | Both member states must have a properly filled ESL/IDK config "file", which contains the identities of the (mocked) DE and DO's of both member states and have registered the proper evidence type supported.
Properly filled SMP | Config | This must be completed before the tests | Both member states must assure they have their DE and DO information (identity, url and evidence type) regsitered in the SMP of eGOVLab
Properly filled SML | Config | This must be completed before the tests | Both member states must assure they have their AS/4 gateways properly regsitered (url, certificate, identifier) in the eGOVLab SML, so their routing informtion can be found by the other AS/4 gateways